## Action Tracker
RSPO ASC Action Tracker Post Sep 2022 Meeting
No | Task/Activities | Topic area | PIC | Status (click on link for reference) | Action received | Action to be completed (timeline agreed) | Next step expected | Comments / Notes | [17 empty] | Weblink to final output(s) (where applicable)
1 | Secretariat to upload accepted minutes on the ASC webpage. | RSPO ASC matters | RSPO Secretariat (AMA) | Done | 2020-03-01 | 2020-03-01 |  |  | Completed | [16 empty] | https://www.rspo.org/resources/supporting-bodies-sc-wg-tf-/standing-committees/assurance-standing-committee/3-minutes-of-meeting
2 | Secretariat to follow up on the RT Prep Clusters format. | RSPO ASC matters | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2020-11-01 |  |  | X | X | X | X | X | X | X | X | Completed
3 | Secretariat to park the budget for ASC Independent Lead and other agreed work plans in the FY21 Budget. | RSPO ASC matters | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
4 | Secretariat to come up with a budget setting flowchart for WGs/TFs. | WG/TF | RSPO Secretariat (BT) | Closed (superceded) | 2020-03-01 | 2021-06-01 |  |  | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | CLOSED
5 | Secretariat to remove the clause on embargo in the ToR and reword the Conflict of Interest clause. | RSPO ASC matters | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
6 | Secretariat to update the ToR on the Contingency Plan. | RSPO ASC matters | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
7 | BT to bring up the proposal of having everyone abide to the common RSPO CoC at the SC Alignment meeting. | RSPO ASC matters | RSPO Secretariat (BT) | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
8 | ASC members to review the Labour Auditing Guidance and engage with their contacts to provide feedback. | Social & Env issue | All ASC Members | Closed (superceded) | 2020-03-01 | 2020-11-01 |  |  | X | X | X | X | X | X | X | X | CLOSED
9 | A TF is to be formed to succeed LTF to address labour issue. | WG/TF | EK, LM, PW | Done | 2020-03-01 | 2020-09-01 |  |  | X | X | X | X | X | X | Completed
10 | Secretariat to look at engaging with WageIndicator to start discussion on labour issues. | Social & Env issue | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2020-09-01 |  |  | X | X | X | X | X | X | Completed
11 | The Labour Auditing Guidance should be reviewed by labour experts and piloted, before it can be endorsed by the ASC. | Social & Env issue | EK, LM, PW | Done | 2020-03-01 |  |  | Field test conducted in MY and ID in Oct 2021. Draft guidance reviewed by Labour Subgroup under the HRWG in March 2022 | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x
12 | PW and MC to reword the proposed solution in their proposal. | Social & Env issue | PW & MC | Done | 2020-03-01 | 2020-06-01 |  |  | X | X | X | Completed
13 | The issues on the firewalling of Complaints Desk, recruitment of CP members and who they report to,will be discussed during the meeting with CP. | ASC/CP | All ASC Members | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
14 | Secretariat to revise the KPIs to include quantitative targets and make changes to some of the wording. | RSPO ASC matters | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2021-04-01 |  |  | X | X | X | X | X | X | X | X | x | x | x | x | x | Completed
15 | ASC members to bring up issues regarding IMU, shared responsibility, recruitment of experts into the CP and the building a pool of experts in the ASC-CP meeting. | ASC/CP | All ASC Members | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
16 | Secretariat to proceed with Adam Harisson’s proposal. | RSPO ASC matters | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
17 | Secretariat to request a more detailed proposal from the Proforest. | RSPO ASC matters | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
18 | Secretariat to send out email to the identified stakeholders informing of the change of dates and location of the first Assurance Forum. | Assurance Forum | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2020-05-01 |  |  | X | X | Completed
19 | Secretariat to look into building a pool of NGOs/experts to report on non-compliances of certified units, in high risk areas. | Social & Env issue | RSPO Secretariat (WM & AMA) | Closed (superceded) | 2020-03-01 | 2020-10-01 |  |  | X | X | X | X | X | X | X | CLOSED
20 | Final comments on ASC ToR and KPIs from ASC members (by 30th June) | RSPO ASC matters | All ASC Members | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
21 | ASC members to give feedbacks to the Labour Auditing Guidance & the Secretariat to follow up on the implementation plan for piloting in the next meeting. | Social & Env issue | All ASC Members | Closed (superceded) | 2020-06-01 | 2020-11-01 | [5 empty] | X | X | X | X | X | CLOSED
22 | ASC members to suggest on the RT prep cluster format (by end of July 2020) | RSPO ASC matters | All ASC Members | Done | 2020-06-01 | 2020-08-01 | [5 empty] | X | X | Completed
23 | The Secretariat will share the independent review report to the Assurance Forum participants prior to the meeting on 26 June 2020. | Assurance Forum | RSPO Secretariat | Done | 2020-06-01 | 2020-06-01 | [5 empty] | Completed
24 | Adam H will incorporate all feedbacks from the ASC Meeting and the Assurance Forum and finalise the report. | RSPO ASC matters | Adam H | Done | 2020-06-01 | 2020-06-01 |  |  | Completed
25 | The Secretariat (supported by the facilitator) will incorporate all comments on ToR and KPIs and get it back out to all ASC members (by 3rd week of July). | RSPO ASC matters | RSPO Secretariat, NJ, SPH | Done | 2020-06-01 | 2020-07-01 | [5 empty] | X | Completed
26 | The Secretariat to share the Certification Systems Document to ASC members. | Certification & CBs | RSPO Secretariat | Done | 2020-06-01 | 2020-09-01 | [5 empty] | X | X | X | Completed
27 | The Secretariat will check with ASI on transparency of the CBs performance. | Certification & CBs | RSPO Secretariat | Done | 2020-06-01 | 2020-11-01 | [5 empty] | X | X | X | X | X | Completed
28 | The Secretariat will update the ASC members on the HRD final report. | Social & Env issue | RSPO Secretariat | Done | 2020-06-01 | 2020-07-01 | [5 empty] | X | Completed
29 | MC & PW will take the decision of the proposal paper to the next Board meeting | Social & Env issue | MC & PW | Done | 2020-06-01 | 2020-09-01 | [8 empty] | Completed
30 | The ASC/Secretariat share the list of the Assurance Forum and re-confirm their involvement. | Assurance Forum | RSPO Secretariat | Done | 2020-06-01 | 2020-12-01 | [5 empty] | X | X | X | X | X | x | Completed
31 | The ASC/Secretariat should include ASI and HCVRN in the Assurance Forum. | Assurance Forum | RSPO Secretariat | Done | 2020-06-01 | 2020-06-01 | [5 empty] | Completed
32 | The ASC/Secretariat will send out MoM | RSPO ASC matters | NJ/SPH | Done | 2020-06-01 | 2020-07-01 | [5 empty] | X | Completed
33 | The ASC/Secretariat will share the proposed roles to the Assurance Forum. | Assurance Forum | RSPO Secretariat | Done | 2020-06-01 | 2020-12-01 | [5 empty] | X | X | X | X | X | X | Completed
34 | The Lead Facilitator will add ‘relationship with HCSA’ included in scope of work in draft ToR, review feedback from ASC members on the draft ToR and distribute final draft of ToR to ASC members via email to sign off. | RSPO ASC matters | NJ/SPH | Done | 2020-09-01 | 2020-10-01 | [8 empty] | X | Completed
35 | The Secretariat will share ASC budget plan and activities for financial year 2020-2021. | RSPO ASC matters | RSPO Secretariat | Done | 2020-09-01 | 2020-10-01 | [8 empty] | X | Completed
36 | The Secretariat will set up a call with Co-Chairs and NJ to review the approved budget and identify any gaps on the resourcing plan for 2020-2021. | RSPO ASC matters | RSPO Secretariat | Done | 2020-09-01 | 2020-10-01 | [8 empty] | X | Completed
37 | AA will discuss all feedback received from ASC members on CBs Performance Assessment document with ASI and share the updates at the next ASC Meeting. | Certification & CBs | RSPO Secretariat | Done | 2020-09-01 | 2020-12-01 | [8 empty] | X | X | X | Completed
38 | The Secretariat will launch Fire Hub by end of Sep 2020 on limited access during a trial period before full access starts. | Social & Env issue | RSPO Secretarit | Closed (superceded) | 2020-09-01 | 2020-10-01 | [8 empty] | X | CLOSED
39 | Co-chairs of the ASC and CP will work together to identify issues for the agenda for the ASC/CP joint meeting. | ASC/CP | Co-Chairs | Done | 2020-09-01 | 2021-05-01 | [8 empty] | X | X | x | x | x | x | x | x | Completed
40 | AA will share the draft SOP for the evaluation of CB’s performance by 20th Nov 2020. | Certification & CBs | RSPO Secretariat | Done | 2020-11-01 | 2020-12-01 | [10 empty] | x | x
41 | NJ & Co-chairs will convene the forming of sub-groups within ASC to look at issues related to ASI and forming the pool of experts. | ASC sub groups | Co-chairs | Done | 2020-11-01 | 2021-05-01 | [10 empty] | x | x | x | x | x | x | Completed
42 | IMU will launch the Hotspots Hub in w/c 9th Nov 2020 | RSPO ASC matters | RSPO Secretariat | Done | 2020-11-01 | 2021-07-01 | [8 empty] | x | x | x | x | x | x | x | x | x | x | Completed
43 | ASC will follow up with HCVRN on the clarity of their role and contribution to ASC works. | RSPO ASC matters | RSPO Secretariat | Done | 2020-11-01 | 2021-03-01 | [10 empty] | x | x | x | x | Completed
44 | The Secretariat to develop ToR to outline scope of root cause analysis and to consider a combination of internal reviews, ASI and external reviews (IUCN reviews) for this work. Overall timeline of up to 12 months is envisaged, with interim feedback/update to ASC during Q1, for discussion at the March 2021 ASC meeting | Gap analysis | RSPO Secretariat | Done | 2020-11-01 | 2020-12-01 | [10 empty] | x | Completed
45 | The Secretariat is to compile a list of existing gaps and other related issues. | Gap analysis | RSPO Secretariat | Closed (superceded) | 2020-11-01 | 2020-12-01 | [10 empty] | x | x
46 | NJ will discuss with The Secretariat and co-Chairs and will update the ASC members on the timeline for the ToR development and plan to move forward. | RSPO ASC matters | NJ, Co-chairs, RSPO Secretariat | Done | 2020-11-01 | 2020-12-01 | [10 empty] | x | Completed
47 | The Secretariat will review outstanding recommendations from the ATF independent review and bring proposed actions back to ASC members before the next meeting. | WG/TF | RSPO Secretariat | Done | 2020-11-01 | 2021-03-01 | [10 empty] | x | x | x | x | Completed
48 | The RaCP report will be made public | Social & Env issue | RSPO Secretariat | Done | 2020-11-01 | 2021-03-01 | [10 empty] | x | x |  |  | Completed
49 | The Secretariat to share RISS monitoring updates by email to get input & feedback from ASC members. | RSPO ASC matters | RSPO Secretariat | Done | 2020-11-01 | 2021-04-01 | [10 empty] | x | x | x | x | x | Completed
50 | The sub-group of ASC will aim to move forward the meeting with CP around 1st or 2nd week of December. | WG/TF | RSPO Secretariat | Closed (superceded) | 2020-11-01 | 2020-12-01 | [10 empty] | x | x
51 | WM will communicate with CP on the meeting schedule. | WG/TF | RSPO Secretariat | Closed (superceded) | 2020-11-01 | 2020-12-01 | [10 empty] | x | x
52 | The Assurance Forum will be conducted around 1st & 2nd week of December. | Assurance Forum | RSPO Secretariat | Done | 2020-11-01 | 2020-12-01 | [10 empty] | x | Completed
53 | NJ will support WM on the coordination of the Assurance Forum. | Assurance Forum | RSPO Secretariat | Done | 2020-11-01 | 2020-12-01 | [10 empty] | x | Completed
54 | The ASC/Secretariat will send out MoM | RSPO ASC matters | NJ/SPH | Done | 2020-11-01 | 2020-12-01 | [10 empty] | x | Completed
55 | NJ will support WM on the coordination of the joint ASC/CP meeting | WG/TF | RSPO Secretariat | Closed (superceded) | 2020-11-01 | 2020-12-01 | [10 empty] | x | x
56 | The Secretariat will look into feedback the proposed Assurance Forum ToR and finalise | Assurance Forum | RSPO Secretariat | Done | 2020-12-01 | 2021-06-01 | [11 empty] | x | x | x | x | x | x | Completed
57 | The Secretariat will share the ASI longer presentation with the Assurance Forum participants | Assurance Forum | RSPO Secretariat | Done | 2020-12-01 | 2020-12-01 | [11 empty] | Completed
58 | The ASC/Secretariat will send out Assurance Forum MoM | Assurance Forum | NJ/SPH | Done | 2020-12-01 | 2021-01-01 | [11 empty] | x | Completed
59 | All Assurance Forum participants to flag up key shortcomings to the Secretariat in addition to what was already highlighted in the ATF review and other reports. | Assurance Forum | AF participants | Done | 2020-12-01 | 2021-04-01 | [11 empty] | x | x |  | x | Completed
60 | The Secretariat will share the update on root cause analysis with ASC members in Q1 2021 at the ASC meeting and at the next Assurance Forum in 2021. | Gap analysis | RSPO Secretariat | Done | 2020-12-01 | 2021-04-01 | [11 empty] | x | x | x | x | Completed
61 | The Secretariat (TR) will follow up on HCVRN role and contribution to ASC work | RSPO ASC matters | RSPO Secretariat | Done | 2020-12-01 | 2021-04-01 | [11 empty] | x | x | x | x | Completed
62 | The Secretariat will follow up on possible date(s) for a joint meeting with CP in April. | WG/TF | RSPO Secretariat | Done | 2020-12-01 | 2021-05-01 | [11 empty] | x | x | x | x | x | Completed
63 | The Secretariat will follow up on the plan to form a sub-group of a pool of experts. | ASC sub groups | RSPO Secretariat | Ongoing | 2020-12-01 |  | No response from Call for Interest for Project MgmtTeam in Sept 2022 (to be discussed at agenda 4.2 - Dec mtg) | [10 empty] | x | x | x | x | x | x | x | x | https://www.rspo.org/news-and-events/announcements/expression-of-interest-project-management-team-for-pool-of-experts
64 | NJ will liaise with TR to share the revised ASI SOP on CB performance analysis with ASC members. | Certification & CBs | NJ & RSPO Secretariat | Done | 2020-12-01 | 2021-01-01 | [12 empty] | Completed
65 | The Secretariat will be in contact with Liberty Shared to review Sime Darby allegations during February 2021. | RSPO ASC matters | RSPO Secretariat | Closed (superceded) | 2020-12-01 | 2021-03-01 | [13 empty] | x | Completed
66 | NJ & Co-chairs to follow up on meeting with HRWG. | WG/TF | NJ & Co-chairs | Done | 2020-12-01 | 2021-03-01 | [14 empty] | completed
67 | The Secretariat will share the report on FGV when finalised | RSPO ASC matters | RSPO Secretariat | Done | 2021-02-01 | 2022-02-01 |  | FGV Post Complaints Monitoring had been completely handed over to the Grievance unit in February 2022. | [11 empty] | x | x | x | x | x | x
68 | At ASC Meeting April 2021: The Secretariat will share the workplan and the first result on the root cause analysis. This will identify priorities to be addressed through ASC SC and sub-groups. | ASC sub groups | RSPO Secretariat | Done | 2021-03-01 | 2021-03-01 | [14 empty] | Completed
69 | At ASC Meeting April 2021: The Secretariat, Co-chairs and NJ will identify possible working groups under the ASC. | ASC sub groups | RSPO Secretariat, Co-chairs, NJ | Done | 2021-03-01 | 2021-04-01 | [14 empty] | x | Completed
70 | The Secretariat will provide a timeline and guidance on the Decent Living Wage (DLW) for certificate holders and the CBs. | Social & Env issue | RSPO Secretariat, Co-chairs, NJ | Done | 2021-03-01 | 2022-08-01 |  | Proposed revision to indicator 6.2.6 incorporated into P&C 2023 draft (new indicator num. 6.3.2) | [12 empty] | x | x | x | x | x
71 | A workshop on gap analysis for ASC members will be scheduled in early May 2021. | Gap analysis | RSPO Secretariat | Done | 2021-04-01 | 2021-05-01 | [15 empty] | x | Completed
72 | All ASC members to send further feedback and input for the draft gap analysis report. | Gap analysis | ASC members | Done | 2021-04-01 | 2021-05-01 | [15 empty] | x | Completed
73 | ASI (HdB) will share SoP of the CABs Performance Appraisal Framework for feedback and input from ASC members. | Certification & CBs | RSPO Secretariat | Done | 2021-04-01 | 2021-04-01 | [15 empty] | x | x | x | x
74 | The Secretariat (TR) will share/discuss the proposal to form a sub-group under ASC to supervise the process on MEL & Impact. | ASC sub groups | RSPO Secretariat | Closed (superceded) | 2021-04-01 |  |  | The Secretariat has decided on move ahead with this process internally, since the work straddles all units and SCs. Periodic updates to be given to the Board and SCs. | [13 empty] | x | x | x | x
75 | TR will revise the grievance systems flowchart for ASC review. | Social & Env issue | RSPO Secretariat | Closed (superceded) | 2021-04-01 | 2021-08-01 | [15 empty] | x | x | x | x
76 | The Secretariat will share the timeline on DLWTF toolkit development, as soon as available. | Social & Env issue | RSPO Secretariat | Ongoing | 2021-04-01 |  | The next DLW TF meeting will be held in December 2022, updates will be given in Q1 2023 ASC meeting | [14 empty] | x | x | x | x
77 | The Secretariat to follow up on the possibility of collaboration with Wage Indicator on DLW. | Social & Env issue | RSPO Secretariat | Ongoing | 2021-04-01 |  | The next DLW TF meeting will be held in December 2022, updates will be given in Q1 2023 ASC meeting | [14 empty] | x | x | x | x
78 | The Secretariat will launch the Fire Hub in June 2021. All ASC members to convey message to give consent for the Fire Hub reporting. | RSPO ASC matters | RSPO Secretariat | Done | 2021-04-01 | 2021-07-01 | [15 empty] | x | x | x | Completed
79 | NJ will seek ASC members’ views on including an SRWG agenda item during the next meeting. | WG/TF | NJ | Done | 2021-04-01 | 2021-07-01 | [15 empty] | x | x | x | Completed
80 | ASC members to discuss and decide in which sub-group the pool of experts should sit and what the reward mechanism is appropriate. | ASC sub groups | ASC members & The Secretariat | Ongoing | 2021-04-01 |  | To be decided once framework has been finalised (related to item 63) | [14 empty] | x | x | x | x
81 | The formation of ASC sub-groups will be based on the results of the root cause analysis, and prioritisation of actions. | ASC sub groups | RSPO Secretariat | Done | 2021-04-01 | 2021-07-01 | [15 empty] | x | x | x | x
82 | HRWG to give regular update to the ASC on ongoing HRWG activities that are relevant to Assurance. | WG/TF | RSPO Secretariat | Ongoing | 2021-04-01 |  | The next HRWG meeting will be held in December 2022. FPIC Guide 2022 was endorsed by the SSC on 16 November 2022. Women Safety Project Strategy Paper will be presented to HRWG for approval. Ongoing discussions in the Labour Subgroup on proposed activities on recruitment fees, social dialogue and training for companies. | [14 empty] | x | x | x | x
83 | ASC will involve HRWG members in its sub-groups and regularly in meetings. | WG/TF | RSPO Secretariat | Closed (superceded) | 2021-04-01 |  | Invite was sent in January, followed up in April, no interest from HRWG members | [14 empty] | x | x | x | x
84 | Members agreed that BHCVWG will now change its reporting line, and sit under the ASC. | WG/TF | ASC members & The Secretariat | Done | 2021-04-01 | [16 empty] | x | x | x | x
85 | CP will track information on how many certified units maintain and lose their certification after complaints are closed. | Remote audit | CP members | Done | 2021-05-01 | [17 empty] | x | x | x
86 | The Secretariat will discuss and consider mechanisms to include the CP in the CAP review process. | CAP review | RSPO Secretariat | Closed (superceded) | 2021-05-01 |  |  | Grievance Unit has been moved to CEO's office on 15 Nov 2021 | [14 empty] | x | x | x
87 | The Secretariat will suggest regular ASC/CP catch up meetings and to include CAP review in the discussion. | CAP review | RSPO Secretariat | Closed (superceded) | 2021-05-01 |  |  | Grievance Unit has been moved to CEO's office on 15 Nov 2021 | [14 empty] | x | x | x
88 | ASC and CP will choose a representative each to be involved in the process to develop the ToR for the CAP review | CAP review | RSPO Secretariat | Done | 2021-05-01 | 2021-08-01 | [16 empty] | x | x | x
89 | Final gap analysis report to provide clear distinctions between evidence-based data, cases studies and allegations. | Gap analysis | RSPO Secretariat | Done | 2021-05-01 | 2021-07-01 | [16 empty] | x | x | Completed
90 | NJ and the Secretariat will share with ASC members on nomination for sub-group to finalise root cause analysis and workplan. This will be brought back to the next ASC meeting. | Gap analysis | RSPO Secretariat & NJ | Done | 2021-05-01 | 2021-07-01 | [16 empty] | x | x | Completed
91 | The root cause analysis report will be shared in the next Assurance Forum. | Gap analysis | RSPO Secretariat | Done | 2021-05-01 | 2021-07-01 | [16 empty] | x | x | Completed
92 | The Secretariat to finalise the nominations for the vacant ASC member seats before the next ASC meeting. | RSPO ASC matters | RSPO Secretariat | Done | 2021-07-01 | 2021-10-01
93 | The Secretariat to circulate draft ToR for CAP Review to the ASC members. | CAP review | RSPO Secretariat | Done | 2021-07-01 | 2021-08-01
94 | The Secretariat will incorporate comments in the gap analysis report on the alignment with CB and growers workshops and on training for growers. | Gap analysis | RSPO Secretariat | Done | 2021-07-01 | 2021-08-01
95 | The Secretariat will share the phasing of activities in the work plan with the ASC members. | Gap analysis | RSPO Secretariat | Done | 2021-07-01 | 2021-10-01
96 | The Secretariat will publish the gap analysis report on the website. | Gap analysis | RSPO Secretariat | Done | 2021-07-01 | 2021-09-01 |  | Report published on website on 2 Sept | [17 empty] | https://rspo.org/library/lib_files/preview/1579
97 | The Secretariat will involve MPOA in the discussion on license extension & remote audits. | Audit & Remote audit | RSPO Secretariat | Done | 2021-07-01 | 2021-09-01 |  | MPOA has been consulted on Scenario 5 Remote Audit draft
98 | The Secretariat will communicate the revised audit scenario 4 and present proposal for scenario 5 in the next ASC meeting in October 2021. | Audit & Remote audit | RSPO Secretariat | Done | 2021-07-01 | 2021-10-01 |  | Contingency Audit Procedure ver 2 published on website on 30 Nov 2021 | [17 empty] | https://www.rspo.org/library/lib_files/preview/1638
99 | The Secretariat will present proposed interim decision to the BHCVWG. Feedback received from BHCVWG will then be shared with the ASC via email to get ASC's approval on interim decision. | WG/TF | RSPO Secretariat | Done | 2021-07-01 | 2021-09-01 |  | Interim decision published on website on 8 Sept 2021 | [17 empty] | https://www.rspo.org/news-and-events/announcements/disclosure-and-continuity-of-certification-for-rspo-pandc-and-rspo-ish-standard
100 | The Secretariat will propose time for a sharing session with HRWG. | WG/TF | RSPO Secretariat | Closed (superceded) | 2021-07-01 | 2021-08-01
101 | MC will follow up with the co-Chair nomination from NGO representative within 2 weeks after the meeting. | RSPO ASC matters | MC | Done | 2021-10-01 | 2021-11-01 |  | Joko Sarjito (interim representative for WWF) has stepped down. New ASC Co-Chair (NGO) is Kamal Seth (new Global Palm Oil Lead for WWF Singapore)
102 | The Secretariat will confirm the designated person who responsible for follow up actions from the RaCP implementation review. | RSPO ASC matter | RSPO Secretariat | Done | 2021-10-01 |  |  | KSL from Biodiversity unit (Standards Division) will be the contact person for progress of RaCP revision
103 | The Secretariat to share plans to form Governance Subgroup to SSC for comments and advice to move forward. | ASC sub-groups | RSPO Secretariat | Done | 2021-10-01 | 2021-10-01
104 | The Secretariat will send out the template sub-group table to get nomination from ASC members until 5th Nov 2021. | ASC sub-groups | RSPO Secretariat | Done | 2021-10-01 | 2021-10-01
105 | The Secretariat to add a step in the remote audit process to accommodate independent sampling to assess effectiveness of remote audits. | Audit & Remote audit | RSPO Secretariat | Done | 2021-10-01 |  |  | Contingency Audit Procedure ver 2 published on website on 30 Nov 2021 | [17 empty] | https://www.rspo.org/library/lib_files/preview/1638
106 | The Secretariat will pass on the proposed solutions on ISH inclusion to the Standard Division. | Certification & CBs | RSPO Secretariat | Done | 2021-10-01 |  |  | Secretariat will work on the relevant guidance, which is to be endorsed by the SHSC
107 | The Secretariat to send Doodle poll to determine the timing for December Assurance Forum. | Assurance Forum | RSPO Secretariat | Done | 2021-10-01 | 2021-11-01
108 | The Secretariat to develop a template for members to request for revisions to their time-bound plan. | Certification & CBs | RSPO Secretariat | Done | 2021-10-01 |  |  | Template was published on the website on 21 Dec 2021 | [17 empty] | https://www.rspo.org/news-and-events/announcements/rspo-announcement-for-time-bound-plan-revision
109 | The Secretariat to seek advice from SSC and prepare an interim solution for ASC's approval. | Certification & CBs | RSPO Secretariat | Done | 2021-10-01 | 2021-11-01
110 | The Secretariat to check with KSL & inform the ASC on progress of RaCP implementation review. | RSPO ASC matter | RSPO Secretariat | Ongoing | 2022-02-01 |  | Draft Remediation and Compensation Procedure (RaCP) Related to Land Clearance Without Prior High Conservation Value (HCV) and High Carbon Stock (HCSA) Assessment is ready and will be presented to the SSC.
111 | The Secretariat to clearly define ISH to avoid confusions with scheme SH and other terms in different NIs. | ISH | RSPO Secretariat | Done | 2022-02-01 |  |  | This was resolved with BoG's endorsement of the RSPO Management System Requirement for Group Certification of FFB on 18 May 2022 (modified on 18 Aug 2022) | [17 empty] | https://www.rspo.org/library/lib_files/preview/1863
112 | The Secretariat to discuss with SDD on recommendations from the independent review of RaCP. | RSPO ASC matter | RSPO Secretariat | Ongoing | 2022-02-01 |  | Draft Remediation and Compensation Procedure (RaCP) Related to Land Clearance Without Prior High Conservation Value (HCV) and High Carbon Stock (HCSA) Assessment is ready and will be presented to the SSC.
113 | The Secretariat to consider synergy between the HCV-HCS guidance and the CB checklist at jurisdictional level. | Certification & CBs | RSPO Secretariat | Ongoing | 2022-02-01 |  | In progress, JA-BHCV WG has started initial discussion | MoU with HCSA is still being finalised
114 | The Secretariat to consider linking the information on CSPK produced and sold from the Dashboard with the CSPKO page on the Impacts section of the website. | Audit & Remote audit | RSPO Secretariat | Ongoing | 2022-02-01 |  | Not started, under the purview of the Certification Unit
115 | The Secretariat to plan for a systemic review of audit system document to come up with an approach to improve the elements and the gaps identified. | Audit & Remote audit | RSPO Secretariat | Ongoing | 2022-02-01 |  | Not started, awaiting result from P&C Review
116 | The Secretariat to confirm the date for the deep-dive session on Labour in March 2022 (with HRWG, to consult with TR). | WG/TF | RSPO Secretariat | Done | 2022-02-01 | 2022-03-01 |  | Draft guidance reviewed by Labour Subgroup under the HRWG in March 2022
117 | The Secretariat to cascade the concerns with the respective personnel working on the Labour Auditing Guidance. | RSPO ASC matter | RSPO Secretariat | Done | 2022-02-01
118 | The Secretariat to revert to ASC member (MC) on the specific subgroup that will discuss CBs performance and independence. | ASC sub-groups | RSPO Secretariat | Done | 2022-02-01 |  |  | Standards Quality Subgroup will discuss this matter and MC has agreed to participate (26 Apr 2022)
119 | The Secretariat to extend the deadline for call of interest for ASC subgroups on the website and provide more clarity on the ToR. | ASC sub-groups | RSPO Secretariat | Done | 2022-02-01 | 2022-03-01 |  | Web call for participation to end on 31 March 2022 (still low interest) | [17 empty] | https://rspo.org/news-and-events/announcements/call-for-participation-in-the-assurance-standing-committee-asc-subgroups
120 | The Secretariat to incorporate the ASC’s comments into the Contingency RSPO Audit Procedure - for Supply Chain Standard (Version 2). | Audit & Remote audit | RSPO Secretariat | Done | 2022-05-01 | 2022-06-01 |  | Document published on 30 June 2022 | [17 empty] | https://rspo.org/news-and-events/announcements/contingency-rspo-audit-procedure-for-supply-chain-standard--updated-version
121 | The Secretariat to channel the ASC’s suggestions on ensuring stakeholders’ confidentiality & safety in remote audits to the P&C Review Task Force. | Audit & Remote audit | RSPO Secretariat | Done | 2022-05-01 | 2022-08-01 |  | WM shared suggestions on 3 Aug 2022
122 | The Secretariat to upload the Assurance Progress report on the ASC webpage | Gap analysis | RSPO Secretariat | Done | 2022-05-01 | 2022-06-01 |  | Report published on the ASC webpage | [17 empty] | https://rspo.org/library/lib_files/preview/1833
123 | The Secretariat to channel feedback from the RSPO ISH Training for Auditors to the Smallholder Unit. | ISH | RSPO Secretariat | Done | 2022-05-01
124 | The Secretariat to channel the ASC’s suggestions on shared learning among growers to the Training Unit under the Technical Division. | Certification & CBs | RSPO Secretariat | Ongoing | 2022-05-01 |  | Action is put on hold until Training Manager is appointed
125 | The GIS team to develop a proposal to improve the sanction mechanism for land clearings on uncertified units. | Certification & CBs | RSPO Secretariat | Ongoing | 2022-05-01 |  | Topic was discussed in the ASC Standards Quality Subgroup meeting on 6 Oct 2022
126 | The GIS team to work with Certification Unit on resolution GA18-2c for deforestation monitoring to enhance the robustness of the Mass Balance model. | Certification & CBs | RSPO Secretariat | Ongoing | 2022-05-01 |  | Proforest has completed the MB Robustness study, which is currently being reviewed by the SSC.
127 | The Secretariat to urgently carry out the actions agreed by the BHCVWG in 2020 to revise the system for identifying and remedying social liabilities. (RaCP Implementation Review) | Certification & CBs | RSPO Secretariat | Ongoing | 2022-05-01 |  | Draft Remediation and Compensation Procedure (RaCP) Related to Land Clearance Without Prior High Conservation Value (HCV) and High Carbon Stock (HCSA) Assessment is ready and will be presented to the SSC.
128 | The Secretariat to send the Secretariat's performance survey to the ASC by 20 May 2022. | RSPO ASC matter | RSPO Secretariat | Done | 2022-05-01 |  |  | Survey sent via SurveyMonkey on 20 May 2022
129 | The Secretariat to consolidate the agenda for the June 2022 ASC-CP meeting. | ASC/CP | RSPO Secretariat | Done | 2022-05-01 | 2022-06-22 |  | Meeting held on 16 June 2022 | [17 empty] | https://rspo.org/library/lib_files/preview/1850
130 | List of action items from ASC-CP Joint Meeting on 16 June 2022: - RSPO will share the number of respondents for each complaint in the analysis. - RSPO team will follow up with details on labour violations and note under which ILO indicators. - The Secretariat to compare ILO requirements with relevant national interpretations in the analysis for complaints related to labour issues. - The Secretariat to clarify which alleged social violations are major or minor and what indicators are being used to identify them. - The Secretariat to set up time to present analysis on RSPO audit’s framework (management system vs performance based). - The Secretariat to share suggestions relating to grievance mechanisms in operating units from this meeting with the P&C Review Task Force. (Done) - The Secretariat to strengthen the auditing for new planting procedures to identify social issues as early as possible. - The Secretariat to share the suggestion with the P&C Review Task Force that supplementary guidance and tools should be launched together with standards revision. (Done) - The Secretariat to develop guidance to increase capacity of auditors for social audit. - The Secretariat will share the list of action points and the next steps, soonest possible. - The Secretariat to set up a quarterly meeting and share relevant documents a week before the meeting. | ASC/CP | RSPO Secretariat | Closed (superceded) | 2022-06-01 |  | Has been discussed at the BoG meeting in June 2022. The following has been agreed: The CP Co-Chairs are to liaise with the ASC Co-Chairs and move this topic of “social auditing concerns" to a more structured discussion under the ambit of the ASC, which can then come up with a solution and recommendation for board consideration. A meeting between ASC & CP Co-Chairs will be organised in Oct 2022 to discuss way forward. | Proposed topics for the ASC-CP Co-Chairs meeting in Oct 2022 were discussed in the Sept meeting.
131 | The Secretariat to incorporate the SSC and ASC’s comments to finalise the Labour Auditing Guidance and publish it on the website as a voluntary guidance document for trial usage of 18 months. | Audit & Remote audit | RSPO Secretariat | Ongoing | 2022-09-01
132 | The Secretariat to develop a ToR for the independent review of the Labour Auditing Guidance prior to the end of the 18 months trial period. | Audit & Remote audit | RSPO Secretariat | Ongoing | 2022-09-01 |  | Not started, pending implementation of the Labour Auditing Guidance
133 | The Certification Unit to revise section 5.7.3 of the Certification Systems Document 2020 to include the statement on minimum 4 estates to be audited, and publish it in the RSPO Interpretation Forum (RIF). | Certification & CBs | RSPO Secretariat | Done | 2022-09-01 |  |  | Revision to 5.7.3 of the CSD 2020 has been done and announcement was made on the RIF on 26 Oct 2022
134 | The Secretariat to discuss with HCVN on a standardised way to monitor HCV areas in RSPO members’ concessions. | ASC sub-groups | RSPO Secretariat | Ongoing | 2022-09-01
135 | The Secretariat to immediately start working on the second study on de-linking CBs with certificate holders. | Audit & Remote audit | RSPO Secretariat | Ongoing | 2022-09-01
136 | The Secretariat to develop a code of conduct for auditors for the next revision of the certification system. | Audit & Remote audit | RSPO Secretariat | Ongoing | 2022-09-01
137 | The Secretariat to organise a physical ASC meeting on 1 December 2022 (during RT 2022). | RSPO ASC matter | RSPO Secretariat | Done | 2022-09-01 |  |  | Meeting will be held on 1 Dec 2022, 930am - 12pm, in hybrid mode (physical at Shangri-La hotel KL, online via Zoom)
138 | The Secretariat to work with the ASC’s Social NGO constituent on draft proposal for improvement on social auditing. | Audit & Remote audit | RSPO Secretariat | Ongoing | 2022-09-01

## Sheet2
Done
Closed (superceded)
Ongoing
ASC sub-groups
ASC/CP
Assurance Forum
CAP review
Certification & CBs
Gap analysis
Audit & Remote audit
RSPO ASC matter
WG/TF
ISH