## Sheet1
Action Tracker Post Nov 2020 Meeting
Action Tracker Guide: - The letter 'X' indicates where we are at the current stage - Once an action has been completed it will be mark with "Completed" labelled in green - Scroll your mouse at the Month Boxes to see updates of the action
| No | Task/Activities | PIC | Status (click on link for reference)
2021
[5 empty] | March | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
| 1 | Secretariat to upload accepted minutes on the ASC webpage. | RSPO Secretariat (AMA) | Done | March: Completed
| 2 | Secretariat to follow up on the RT Prep Clusters format. | RSPO Secretariat (WM & AMA) | Ongoing | bar: March to Oct
| 3 | Secretariat to park the budget for ASC Independent Lead and other agreed work plans in the FY21 Budget. | RSPO Secretariat (WM & AMA) | Done | March: Completed
| 4 | Secretariat to come up with a budget setting flowchart for WGs/TFs. | RSPO Secretariat (BT) | Ongoing | bar: March to Oct
| 5 | Secretariat to remove the clause on embargo in the ToR and reword the Conflict of Interest clause. | RSPO Secretariat (WM & AMA) | Done | March: Completed
| 6 | Secretariat to update the ToR on the Contingency Plan. | RSPO Secretariat (WM & AMA) | Done | March: Completed
| 7 | BT to bring up the proposal of having everyone abide to the common RSPO CoC at the SC Alignment meeting. | RSPO Secretariat (BT) | Done | March: Completed
| 8 | ASC members to review the Labour Auditing Guidance and engage with their contacts to provide feedback. | All ASC Members | Ongoing | bar: March to Oct
| 9 | A TF is to be formed to succeed LTF to address labour issue. | EK, LM, PW | Done | March: X; Apr: X; May: X; Jun: X; Jul: X; Aug: X; Sept: Completed
| 10 | Secretariat to look at engaging with WageIndicator to start discussion on labour issues. | RSPO Secretariat (WM & AMA) | Done | March: X; Apr: X; May: X; Jun: X; Jul: X; Aug: X; Sept: Completed
| 11 | The Labour Auditing Guidance should be reviewed by labour experts and piloted, before it can be endorsed by the ASC. | EK, LM, PW | Ongoing | bar: March to Oct
| 12 | PW and MC to reword the proposed solution in their proposal. | PW & MC | Done | March: X; Apr: X; May: X; Jun: Completed
| 13 | The issues on the firewalling of Complaints Desk, recruitment of CP members and who they report to,will be discussed during the meeting with CP. | All ASC Members | Done | March: Completed
| 14 | Secretariat to revise the KPIs to include quantitative targets and make changes to some of the wording. | RSPO Secretariat (WM & AMA) | Ongoing | bar: March to Oct
| 15 | ASC members to bring up issues regarding IMU, shared responsibility, recruitment of experts into the CP and the building a pool of experts in the ASC-CP meeting. | All ASC Members | Done | March: Completed
| 16 | Secretariat to proceed with Adam Harisson’s proposal. | RSPO Secretariat (WM & AMA) | Done | March: Completed
| 17 | Secretariat to request a more detailed proposal from the Proforest. | RSPO Secretariat (WM & AMA) | Done | March: Completed
| 18 | Secretariat to send out email to the identified stakeholders informing of the change of dates and location of the first Assurance Forum. | RSPO Secretariat (WM & AMA) | Done | March: X; Apr: X; May: Completed
| 19 | Secretariat to look into building a pool of NGOs/experts to report on non-compliances of certified units, in high risk areas. | RSPO Secretariat (WM & AMA) | Ongoing | bar: March to Oct
| 20 | Final comments on ASC ToR and KPIs from ASC members (by 30th June) | All ASC Members | Done | March: Completed
| 21 | ASC members to give feedbacks to the Labour Auditing Guidance & the Secretariat to follow up on the implementation plan for piloting in the next meeting. | All ASC Members | Ongoing | bar: Jun to Oct
| 22 | ASC members to suggest on the RT prep cluster format (by end of July 2020) | All ASC Members | Done | Jun: X; Jul: X; Aug: Completed
| 23 | The Secretariat will share the independent review report to the Assurance Forum participants prior to the meeting on 26 June 2020. | RSPO Secretariat |  | Jun: Completed
| 24 | Adam H will incorporate all feedbacks from the ASC Meeting and the Assurance Forum and finalise the report. | Adam H | Done | March: Completed
| 25 | The Secretariat (supported by the facilitator) will incorporate all comments on ToR and KPIs and get it back out to all ASC members (by 3rd week of July). | RSPO Secretariat, NJ, SPH | Done | Jun: X; Jul: Completed
| 26 | The Secretariat to share the Certification Systems Document to ASC members. | RSPO Secretariat | Done | Jun: X; Jul: X; Aug: X; Sept: Completed
| 27 | The Secretariat will check with ASI on transparency of the CBs performance. | RSPO Secretariat | Ongoing | bar: Jun to Oct
| 28 | The Secretariat will update the ASC members on the HRD final report. | RSPO Secretariat | Done | Jun: X; Jul: Completed
| 29 | MC & PW will take the decision of the proposal paper to the next Board meeting | MC & PW |  | Sept: Completed
| 30 | The ASC/Secretariat share the list of the Assurance Forum and re-confirm their involvement. | RSPO Secretariat | Done | Jun: X; Jul: X; Aug: X; Sept: X; Oct: X; Nov: x; Dec: Completed
| 31 | The ASC/Secretariat should include ASI and HCVRN in the Assurance Forum. | RSPO Secretariat | Done | Jun: Completed
| 32 | The ASC/Secretariat will send out MoM | NJ/SPH | Done | Jun: X; Jul: Completed
| 33 | The ASC/Secretariat will share the proposed roles to the Assurance Forum. | RSPO Secretariat | Ongoing | bar: Jun to Oct
| 34 | The Lead Facilitator will add ‘relationship with HCSA’ included in scope of work in draft ToR, review feedback from ASC members on the draft ToR and distribute final draft of ToR to ASC members via email to sign off. | NJ/SPH | Done | Sept: X; Oct: Completed
| 35 | The Secretariat will share ASC budget plan and activities for financial year 2020-2021. | RSPO Secretariat | Done | Sept: X; Oct: Completed
| 36 | The Secretariat will set up a call with Co-Chairs and NJ to review the approved budget and identify any gaps on the resourcing plan for 2020-2021. | RSPO Secretariat | Done | Sept: X; Oct: Completed
| 37 | AA will discuss all feedback received from ASC members on CBs Performance Assessment document with ASI and share the updates at the next ASC Meeting. | RSPO Secretariat | Ongoing | bar: Sept to Nov
| 38 | The Secretariat will launch Fire Hub by end of Sep 2020 on limited access during a trial period before full access starts. | RSPO Secretarit | Ongoing | bar: Sept to Oct
| 39 | Co-chairs of the ASC and CP will work together to identify issues for the agenda for the ASC/CP joint meeting. | Co-Chairs | Ongoing | bar: Sept to Oct
| 40 | AA will share the draft SOP for the evaluation of CB’s performance by 20th Nov 2020. | RSPO Secretariat | Ongoing | bar: Nov to Dec
| 41 | NJ & Co-chairs will convene the forming of sub-groups within ASC to look at issues related to ASI and forming the pool of experts. | Co-chairs | Ongoing | bar: Nov to Dec
| 42 | IMU will launch the Fire Hub in w/c 9th Nov 2020 | RSPO Secretariat
| 43 | ASC will follow up with HCVRN on the clarity of their role and contribution to ASC works. | RSPO Secretariat | Ongoing | bar: Nov to Dec
| 44 | The Secretariat to develop ToR to outline scope of root cause analysis and to consider a combination of internal reviews, ASI and external reviews (IUCN reviews) for this work. Overall timeline of up to 12 months is envisaged, with interim feedback/update to ASC during Q1, for discussion at the March 2021 ASC meeting | RSPO Secretariat | Done | Nov: x; Dec: Completed
| 45 | The Secretariat is to compile a list of existing gaps and other related issues. | RSPO Secretariat | Ongoing | bar: Nov to Dec
| 46 | NJ will discuss with The Secretariat and co-Chairs and will update the ASC members on the timeline for the ToR development and plan to move forward. | NJ, Co-chairs, RSPO Secretariat | Done | Nov: x; Dec: Completed
| 47 | The Secretariat will review outstanding recommendations from the ATF independent review and bring proposed actions back to ASC members before the next meeting. | RSPO Secretariat | Ongoing | bar: Nov to 2021 Feb
| 48 | The RaCP report will be made public | RSPO Secretariat | Ongoing | bar: Nov to Dec
| 49 | The Secretariat to share RISS monitoring updates by email to get input & feedback from ASC members. | RSPO Secretariat | Ongoing | bar: Nov to Dec
| 50 | The sub-group of ASC will aim to move forward the meeting with CP around 1st or 2nd week of December. | RSPO Secretariat | Ongoing | bar: Nov to Dec
| 51 | WM will communicate with CP on the meeting schedule. | RSPO Secretariat | Ongoing | bar: Nov to Dec
| 52 | The Assurance Forum will be conducted around 1st & 2nd week of December. | RSPO Secretariat | Done | Nov: x; Dec: Completed
| 53 | NJ will support WM on the coordination of both CP meeting and the Assurance Forum. | RSPO Secretariat | Ongoing | bar: Nov to 2021 Feb
| 54 | The ASC/Secretariat will send out MoM | NJ/SPH | Done | Nov: x; Dec: Completed
55
56